## Tickets
INC# | Priority | Site | Type | Status | FE Scheduled | FE Assigned | Description | Logg
| Sev.2 | Regus Ringvägen Stockholm | Installation | Dispatched | 2019-11-14 12:00 | Per Orest | Start to install APs/Skift from allready installed APs !
#1293655 | Sev.2 | Regus Norra Bantorget | BreakAndFix | Dispatched | 2019-11-13 09:00 | Jones Moti | Incident 1293655 - 4348 - STOCKHOLM, NORRA BANTORGET Montera APs och heatmap | 2 more APS to reatche and 3 Somnos speakers to be installed !
#1379130 / 568 | Sev.1 | Regus Stureplan | BreakAndFix | Dispatched | 2019-11-07 09:00 | Jones Moti | Removal of Clients IT Equipments, day3 !
#1339825 | Sev.2 | Regus Norra Bantorget | BreakAndFix | Recieved |  | - - | Request for Wifi Survey - this is a heads up, we don't have the PO yet but will ask to schedule a wifi survey once we have it.
#1305137 | Sev.3 | Stockholm Central | Installation | Recieved |  | Per Orest | Tech Dispatch to Install Printer Driver | > for re-visit
#1293655 | Sev.3 | Regus Norra Bantorget | Installation | Recieved |  | Per Orest | Tech dispatch to install wallport | > Follow-up job from the centre team. Please send us costing.
#1319579 | Sev.2 | Regus Alvik | Installation | Recieved |  | Per Orest | Request For Wall Jack Ports | > We have the PO. Please schedule visit.
#1350962 | Sev.3 | Regus Beskow | Installation | Recieved |  | Per Orest | Office Ports Installation | > Waiting for the costing
#Closure / 568 | Sev.1 | Regus Stureplan | CLS | Solved | 2019-11-15 09:00 | Per Orest | Project type: CLS Centre no.: 568 Centre name: Stockholm Stureplan Site address: Stureplan 4c, 4th floor Start date: 11/15/2019 End date: 11/15/2019 | The site is taken down and all equipment is packed to be shiped to storage | CLS done !
#1357902 | Sev.2 | Stockholm Central | Installation | Solved | 2019-11-06 16:00 | Per Orest | Request For Tech Dispatch To Install New Computer & Cable Management In The Reception Area | > PO has been approved and centre team mentioned that they spoke with Per last week and told them this will be done in 2 weeks. Can you confirm date and time, please? > Fixed the Cablemanagement and mounted the new PC ! | Cablemanagement done, PC Installed. One Wooden socket to be delivered !
#1379130 / 568 | Sev.1 | Regus Stureplan | BreakAndFix | Solved | 2019-11-06 09:00 | Jones Moti | Removal of Clients IT Equipments, day2 ! | This ticket is the 2.ond section of this move of customer ! | All done for to day, new jobb to morrow starting 09:00 !
#1379130 / 568 | Sev.1 | Regus Stureplan | BreakAndFix | Solved | 2019-11-05 14:00 | Jones Moti | Removal of Clients IT Equipments | Helped the Client with some repatching ! | All done for to day, new jobb to morrow starting 09:00 !
#1326249 | Sev.2 | Regus Solna Businesspark | BreakAndFix | Solved | 2019-11-04 10:00 | Per Orest | Tech Dispatch To Do WiFi Survey For Possible Meraki Upgrade | > Waiting for date > Date set to 20191104:1000 >After scanning the WiFi I´ve come to the conclution that this WLAN needs an upgrade ! | Upgrade from 12 APs of model AIR-LAP 1131 AG to Meraki and Add a patchpanel in the commsroom dedicated to the WLAN. The APs is not patched just cabled with cables from the nearest jacket or the commsroom "50meter cabling " in some cases !
NCO5195 | Sev.1 | Epic Spaces Malmö | NCO | Solved | 2019-10-28 08:00 | Per Orest | NCO5195 Malmö Spaces
#1355835 / 3684 | Sev.1 | Regus Beskow | BreakAndFix | Solved | 2019-10-25 10:00 | Per Orest | Btw, I emailed you for this request INCIDENT #1355835 / 3684 - STOCKHOLM, Beskow / Cabling Issue Can you schedule an onsite visit asap, please? | >Located the office that where in use and its not yet patched in to the SW, due to rebuildings in the house ! | > Wait for the contractors to finnish and acually move in to the building, Tumblare Buss are due to move in 2020-01-01 !
#1178868 | Sev.2 | Regus Beskow | Installation | Solved | 2019-10-01 14:30 | Per Orest | Install an WIiFi AP at the 3:rd floor | >Installed a WIiFi AP at the 3:rd floor >There still needs to be an cablemanagement list added on the wall ! | Installed a WIiFi AP at the 3:rd floor
#1310581 | Sev.2 | Regus Ringvägen Stockholm | Installation | Solved | 2019-09-18 08:00 | Per Orest | Installed 4 WePrecent and did some cablemanagement, Installed a Cisco 2960 in the CommsRoom. | Installed 4 WePrecent and did some cablemanagement, Installed a Cisco 2960 in the CommsRoom. | Installed 4 WePrecent and did some cablemanagement, Installed a Cisco 2960 in the CommsRoom.
#1250183 | Sev.2 | Regus Ringvägen Stockholm | BreakAndFix | Solved | 2019-09-11 09:00 | Per Orest | FaultTrace of FAX connection + Cablemanagement | Cablemanagement done, Faulty FAX connection solved | Repatched the cabling betwine Commsrooms
#1137376 | Sev.2 | Regus Stureplan | Installation | Solved | 2019-07-22 12:00 | Per Orest | Install 2x Sonos | Tryed to install 2x sonos but failed due to bad management of the LAN/WAN ! | Centre are to be taken down !
#1137376 | Sev.2 | Regus Stureplan | Installation | Solved | 2019-07-15 09:00 | Per Orest | Install 2xSonos, took One to the lab and configured it for Reception, The fact is that if we don´t get a Tech, we can´t do this OnSite ! | Managed to set up the Sonos speakers ! | Managed to set up the Sonos speakers !
#123459 | Sev.1 | Regus Kista One | BreakAndFix | Solved | 2019-07-01 09:45 | Per Orest | Internet connection down, suspects Clavister FW ! | Picked up a Clavister E80 at centre 4444. moved to centre 4134. On site 4134 11:45 to start my work. Replaced the faulty E80 and remounted the replacement FW, work finished 13:45 local time. | Picked up a Clavister E80 at centre 4444. moved to centre 4134. On site 4134 11:45 to start my work. Replaced the faulty E80 and remounted the replacement FW, work finished 13:45 local time.
#123458 | Sev.1 | Regus Alvik | Installation | Solved | 2019-06-28 15:45 | Per Orest | Zip trunk migration | >Trunk tested OK and working 20:00, left site 20:30 after some fixes | >Trunk tested OK and working
#123457 | Sev.2 | Regus Ringvägen Stockholm | BreakAndFix | Solved | 2019-06-25 13:50 | Per Orest | Tested Aritame installation over the Phone | Tested Aritame installation over the Phone | Airtame tested OK
#123456 | Sev.2 | Regus Ringvägen Stockholm | BreakAndFix | Solved | 2019-06-19 12:15 | Per Orest | WiFiSurvey In Netspot Floor9 & 10 |  | WiFiSurvey In Netspot Floor9 & 10
#123455 | Sev.2 | Regus Norra Bantorget | Installation | Solved | 2019-06-14 08:00 | Per Orest | Patched 6 ports from floor 5 to 4, rebuilt 3 workstations | Patched 6 ports from floor 5 to 4, rebuilt 3 workstations | Patched 6 ports from floor 5 to 4, rebuilt 3 workstations
#123454 | Sev.2 | Regus Ringvägen Stockholm | BreakAndFix | Solved | 2019-06-13 08:50 | Per Orest | • Fit Out and Refurbishment • Other Fitout and Refurbishment costs , Install and take into production ( 4 AIRTIME Dongles)
#123453 | Sev.2 | Regus Ringvägen Stockholm | BreakAndFix | Solved | 2019-06-05 12:00 | Per Orest | WiFiSurvey + Fault search on WiFi | Preformed a WiFiSurvey + Fault search on WiFi

## TimeReports
Status | Type | INC# | Site | Emloyee | Shift started | Shift ended | Hours worked
Created | Time report | #Closure / 568 | Regus Stureplan | Per Orest | 2019-11-15 09:00 | 2019-11-15 20:00 | 10 | Edit Details Delete
Created | Time report | #1357902 | Stockholm Central | Per Orest | 2019-11-06 15:00 | 2019-11-06 20:00 | 5 | Edit Details Delete
Created | Time report | #1326249 | Regus Solna Businesspark | Per Orest | 2019-11-04 10:00 | 2019-11-04 15:00 | 5 | Edit Details Delete
Created | Time report | NCO5195 | Epic Spaces Malmö | Per Orest | 2019-10-28 08:00 | 2019-10-31 15:30 | 45 | Edit Details Delete
Created | Time report | #1355835 / 3684 | Regus Beskow | Per Orest | 2019-10-25 10:00 | 2019-10-25 13:30 | 3.5 | Edit Details Delete
Created | Time report | #1178868 | Regus Beskow | Per Orest | 2019-10-01 14:30 | 2019-10-01 17:30 | 3 | Edit Details Delete
Created | Time report | #1310581 | Regus Ringvägen Stockholm | Per Orest | 2019-09-18 08:00 | 2019-09-18 16:00 | 8 | Edit Details Delete
Created | Time report | #1250183 | Regus Ringvägen Stockholm | Per Orest | 2019-09-11 09:00 | 2019-09-11 15:00 | 6 | Edit Details Delete
Created | Time report | #1137376 | Regus Stureplan | Per Orest | 2019-07-22 12:00 | 2019-07-22 16:30 | 4.5 | Edit Details Delete
Created | Time report | #1137376 | Regus Stureplan | Per Orest | 2019-07-15 09:00 | 2019-07-15 11:00 | 2 | Edit Details Delete
Created | Time report | #1339825 | Regus Norra Bantorget | Per Orest | 2019-07-01 08:45 | 2019-07-01 13:45 | 5 | Edit Details Delete
Created | Time report | #123458 | Regus Alvik | Per Orest | 2019-06-28 15:45 | 2019-06-28 20:30 | 4.75 | Edit Details Delete
Created | Time report | #123457 | Regus Ringvägen Stockholm | Per Orest | 2019-06-25 13:50 | 2019-06-05 14:50 | 1 | Edit Details Delete
Created | Time report | #123456 | Regus Ringvägen Stockholm | Per Orest | 2019-06-19 12:15 | 2019-06-19 15:45 | 3.5 | Edit Details Delete
Created | Time report | #123454 | Regus Ringvägen Stockholm | Per Orest | 2019-06-13 08:50 | 2019-06-13 13:20 | 4.5 | Edit Details Delete
Created | Time report | #123453 | Regus Ringvägen Stockholm | Per Orest | 2019-06-05 12:00 | 2019-06-05 16:00 | 4 | Edit Details Delete
Created | Time report | #123455 | Regus Norra Bantorget | Per Orest | 2016-06-14 08:00 | 2016-06-14 11:00 | 3
Created | Time report | #1379130 / 568 | Regus Stureplan | Jones Moti | 2019-11-06 09:00 | 2019-11-06 17:00 | 8 | Edit Details Delete
Created | Time report | #1379130 / 568 | Regus Stureplan | Jones Moti | 2019-11-05 14:00 | 2019-11-05 17:00 | 3